## Index
Overview
This document will assist your organization to develop and implement a tobacco-free campus policy and provide tobacco cessation services and resources for your clients and employees.
Within this spreadsheet, you will find four tabs highlighting the various stages from policy development to program monitoring and evaluation. Each tab can be quickly accessed by clicking on the links under the Index. Each tab lists tasks needed to complete the activity along with a timeline to gauge when each task should be completed. Each tab has a Completed Date column to help track when tasks have been completed. The final tab is a Complete Timeline which consolidates each activity into one comprehensive timeline.
Within each timeline, various tasks are linked to a file sharing server with documents and resources to provide examples and supporting documentation to help you complete this task. You can access the resources by double clicking on the specific task.
Index
Policy Development
Organizational Preparation
Policy Implementation
Program Monitoring and Evaluation
Complete Timeline
Useful Links
LMHA Participation Agreement
Tobacco Free Campus and Tobacco Cessation Program Index

## Policy Development
Date Task Completed | TTTF Tasks | Six months | Four months | Two months | One month | Two weeks | One week | Quit Date
Select employee lead for TFC project and develop workgroup
Possible work group composition: Project Lead, Executive Member, Nursing, HR, Medical Records, Marketing/Communications, Facilities
Explore possible options for tobacco-free policy (w/assistance of TTTF team)
Reference toolkit resources for sample tobacco-free worksite policies www.takingtexastobaccofree.com
Contact TTTF staff for technical assistance with crafting policy language
Draft tobacco-free campus policy that includes organization TFC date and procedures for ongoing surveillance, monitoring, HR processes, and quarterly reporting
Submit draft tobacco-free worksite policy using existing P&P process
Tobacco Free Campus Policy Development Timeline

## Organizational Preparation
Date Task Completed | TTTF Tasks | Six months | Four months | Two months | One month | Two weeks | One week | Quit Date
As soon as policy is signed, communicate the new policy to all employees, community partners, clients, and other vested groups and outline upcoming process to become a TFC (communication will be an ongoing process between now and effective TFC date)
Internal communication can include: email blast, staff meetings, newsletters, staff training, interoffice memos, screensavers, table tents
Create media/publicity on TFC policy adoption, community notices, and quit date - celebrate successful quit stories
Create and select language and graphics for internal and external signage & promotional materials
Take inventory of number of external signs needed
Meet with HR regarding NRT/medications covered under health benefits and, if possible, provide coverage for cessation aids not covered by insurance
Meet with MIS to integrate tobacco use assessment into EMR (if applicable)
Meet with MIS to integrate coding and billing for tobacco cessation services into EMR (if applicable)
Meet with Pharmacy/Nursing director regarding process and procedures to provide NRT to clients and employees
Create signage informing employees, clients and visitors of new TFC policy for waiting areas, break rooms, restrooms, etc.
Begin process to have permanent signs produced – work with facilities and sign company on installation before quit date
Design and order all promotional materials for policy implementation (water bottles, stress balls/hearts, sticky notes, t-shirts, buttons, hand sanitizers, etc.), if appicable
Continue to communicate TFC policy to employees, clients, visitors, and potential clients
Communicate tobacco cessation resources and services available to employees and clients
Continue to communicate TFC policy to all community partners and other vested groups
Begin ordering all print materials for policy education - e.g. TFC reminder cards, training materials for employees, hand outs for consumers, tobacco cessation resources/materials, quit date celebration signage, etc.
Select and order new trash receptacles, if needed
Revise contracts with vendors, if needed, and communicate policy with all vendors
Create website (internal and external) with information on policy and cessation resources
TUA integrated in EMR, if applicable
Communicate TUA integration into EMR, provide training on how to document tobacco use in EMR
Meet with various departments/units/teams to educate on TFC policy, TUA, and cessation resources
Solicit questions/concerns/comments about policy and post on website & Q&A emails
Incorporate tobacco-free worksite policy information into New Employee Orientation
Create employee TFC policy acknowledgment statement (have all current and new employees sign statement)
Distribute all print materials to all various departments/units/teams
Email Q&A’s to employees about policy and cessation resources
Begin to install permanent signage outside – ensure signage is in place prior to implementation date
Remove all cigarette receptacles – install new trash receptacles, if had ash trays on them
Tobacco Free Campus Organizational Preparation

## Policy Implementation
Date Task Completed | TTTF Tasks | Six months | Four months | Two months | One month | Two weeks | One week | Quit Date | One week
Create media/publicity on TFC policy adoption, community notices, and quit date - celebrate successful quit stories
Celebration at each site – wear buttons/t-shirts, distribute promotional materials to clients, visitors, etc.
Ensure that all employees are enforcing the TFC policy
Bring employee violations to supervisors attention – address with employee
Ensure trash receptacles and permanent signage are in place at all sites
Ashtrays are removed from all sites
Distribute NRT to all clients interested in quitting
Begin to assess all clients for tobacco use (if not already in place)
Tobacco Free Campus Policy Implementation

## Monitoring and Evaluation
Date Task Completed | TTTF Tasks | Six months | Four months | Two months | One month | Two weeks | One week | Quit Date | One week | One month | Three months | Six months | One Year
Ensure all employees are enforcing TFC policy
Bring employee violations to supervisors attention
Continue to inform employees on TFC policy, compliance concerns and updates, highlight cessation opportunities and successful quit efforts
Conduct chart audits to ensure TUA is being completed
Conduct chart audit for cessation referral documentation and NRT/medication assistance
Conduct environmental scan of grounds and have conversations with employees about TFC policy and compliance issues
Tobacco Free Campus Monitoring and Evaluation

## Complete Timeline
Date Task Completed | TTTF Tasks | Six months | Four months | Two months | One month | Two weeks | One week | Quit Date | One week | One month | Three months | Six months | One Year
Select employee lead for TFC project and develop workgroup
Possible work group composition: Project Lead, Executive Member, Nursing, HR, Medical Records, Marketing/Communications, Facilities
Explore possible options for tobacco-free policy (w/assistance of TTTF team)
Reference toolkit resources for sample tobacco-free worksite policies www.takingtexastobaccofree.com
Contact TTTF staff for technical assistance with crafting policy language
Draft tobacco-free campus policy that includes organization TFC date and procedures for ongoing surveillance, monitoring, HR processes, and quarterly reporting
Submit draft tobacco-free worksite policy using existing P&P process
As soon as policy is signed, communicate the new policy to all employees, community partners, clients, and other vested groups and outline upcoming process to become a TFC (communication will be an ongoing process between now and effective TFC date)
Internal communication can include: email blast, staff meetings, newsletters, staff training, interoffice memos, screensavers, table tents
Create media/publicity on TFC policy adoption, community notices, and quit date - celebrate successful quit stories
Create and select language and graphics for internal and external signage & promotional materials
Take inventory of number of external signs needed
Meet with HR regarding NRT/medications covered under health benefits and, if possible, provide coverage for cessation aids not covered by insurance
Meet with MIS to integrate tobacco use assessment into EMR (if applicable)
Meet with MIS to integrate coding and billing for tobacco cessation services into EMR (if applicable)
Meet with Pharmacy/Nursing director regarding process and procedures to provide NRT to clients and employees
Create signage informing employees, clients and visitors of new TFC policy for waiting areas, break rooms, restrooms, etc.
Begin process to have permanent signs produced – work with facilities and sign company on installation before quit date
Design and order all promotional materials for policy implementation (water bottles, stress balls/hearts, sticky notes, t-shirts, buttons, hand sanitizers, etc.), if appicable
Continue to communicate TFC policy to employees, clients, visitors, and potential clients
Communicate tobacco cessation resources and services available to employees and clients
Continue to communicate TFC policy to all community partners and other vested groups
Begin ordering all print materials for policy education - e.g. TFC reminder cards, training materials for employees, hand outs for consumers, tobacco cessation resources/materials, quit date celebration signage, etc.
Select and order new trash receptacles, if needed
Revise contracts with vendors, if needed, and communicate policy with all vendors
Create website (internal and external) with information on policy and cessation resources
TUA integrated in EMR, if applicable
Communicate TUA integration into EMR, provide training on how to document tobacco use in EMR
Meet with various departments/units/teams to educate on TFC policy, TUA, and cessation resources
Solicit questions/concerns/comments about policy and post on website & Q&A emails
Incorporate tobacco-free worksite policy information into New Employee Orientation
Create employee TFC policy acknowledgment statement (have all current and new employees sign statement)
Distribute all print materials to all various departments/units/teams
Email Q&A’s to employees about policy and cessation resources
Begin to install permanent signage outside – ensure signage is in place prior to implementation date
Remove all cigarette receptacles – install new trash receptacles, if had ash trays on them
Create media/publicity on TFC policy adoption, community notices, and quit date - celebrate successful quit stories
Celebration at each site – wear buttons/t-shirts, distribute promotional materials to clients, visitors, etc.
Ensure that all employees are enforcing the TFC policy
Bring employee violations to supervisors attention – address with employee
Ensure trash receptacles and permanent signage are in place at all sites
Ashtrays are removed from all sites
Distribute NRT to all clients interested in quitting
Begin to assess all clients for tobacco use (if not already in place)
Ensure all employees are enforcing TFC policy
Bring employee violations to supervisors attention
Continue to inform employees on TFC policy, compliance concerns and updates, highlight cessation opportunities and successful quit efforts
Conduct chart audits to ensure TUA is being completed
Conduct chart audit for cessation referral documentation and NRT/medication assistance
Conduct environmental scan of grounds and have conversations with employees about TFC policy and compliance issues
Tobacco Free Campus Complete Timeline

## Useful Links
Below are a variety of useful websites and pdf documents from various soruces to assist you with your tobacco-free campus policy and offering tobacco cessation to clients and employees.
Websites
Office of the U.S. Surgeon General
BeTobaccoFree.gov
CDC- Tobacco-free Campus
Smoking Cessation Leadership Center (Mental Health and Substance Abuse)
Treating Tobacco Use and Dependence: Clinical Practice Guidelines
Become An EX Smoker
Americans for Non-Smoker's Rights
Yes You Can! Texas QuitLine
SAMHSA - Smoking and Mental Illness
Society for Research on Nicotine and Tobacco
Ask and Act
Cease Smoking Today
A Toolkit for Substance Abuse Treatment Providers
Useful Websites and Resources

## Participation Agreement
CPRIT Prevention grant
Tobacco Free LMha’s
By The University of Texas MD Anderson Cancer Center, University of Houston and ATCIC
LMHA Participation Agreement
Overview
The University of Texas MD Anderson Cancer Center, The University of Houston, and the ATCIC have received an Evidence-Based Cancer Prevention Services Grant from the Cancer Prevention Institute of Texas (CPRIT) to help disseminate a multi-pronged Tobacco-Free Workplace Program to selected Texas LMHA’s. The grant will provide training/education, consultation, policy assistance, treatment resources, and practical guidance, as needed, to both implement and sustain the changes that will result in the long-term prevention of tobacco-related cancers among consumers, employees, and the larger communities in which they live.
This award offers a tremendous opportunity to capitalize upon state mandates for tobacco-free campus policies by aiding LMHA’s to implement a more comprehensive evidence-based tobacco-free workplace program that includes education, screening, treatment, and outreach components in addition to the tobacco-free campus policy. Increasing tobacco cessation rates is critically important to the advancement of cancer prevention in Texas, and we hope you will join us in achieving this important goal of improving the health of the Texans we employ and serve.
Participation Requirements
Participating LMHA Agrees To The Following:
· Identify one (or more) internal employee/s who will work as a project manager/clinic champion and collaborate closely with the project team to implement the policy and training required to take the LMHA tobacco free.
· Make employees (including physicians) available for our training program.
· Make all employees available for re-training, as necessary.
· Integrate regular Tobacco use Assessments (TUA) into the consumer assessment process with the help of the project team, so that tobacco screening is occurring at every consumer contact.
· Develop and implement a tobacco free campus policy that includes electronic cigarettes.
· Set an organization “Quit Date” and go tobacco free on that date.
· Have a fully-implemented multi-component Tobacco-Free Workplace Program in place by the end of the implementation period.
· Agree to include tobacco education at all new employee orientations.
· Share generic organizational level TUA data on staff and consumers.
· Make available the Nicotine Replacement Therapies (NRT’s) provided through the grant to staff and consumers.
· Work with the project team to identify ongoing sources of funding to support the provision of NRT for consumers and employees.
· Participate in all aspects of the grant elements (i.e., training, consultation, technical assistance, NRT’s, data collection, follow up).
· Properly record and regularly provide data to the project team that is essential to the evaluation strategy and continue to monitor these factors beyond the grant funding period.
· Maintain one or more clinic champions for the program in each clinic beyond the funding period to serve as a consultant and to devote a portion of service time to sustainability maintenance.
· Make TUAs and tobacco use cessation resources an ongoing change to their systems that will persist beyond the grant funding period.
· Work with project team to develop a strategy for including community stakeholders in training and in ongoing communication.
___________________________________________________________
LMHA CEO | Date
Tobacco Free Campus Complete Timeline